## List1
Questions | SUB questions | Type of SQ | Measure or indicators | Target or standard (if normative) | Baseline data? | Data Sources | Design | Sample | Data collection Instrument | Data Analysis | Comments
1. How were the beneficiaries selected? |  | D
| 1.A. How was the threshold determined? | D | Comparison with evaluation of similar project Triangulation | Na | Yes | * Project management team * Rules and procedures on who qualifies, - internal manual | Non-experimental design Case study | Non-Random sample | Semi structured interviews, desk study | Qualitative, content analysis
| 1.B. What were the criteria for selection ? | D | Comparison with evaluation of similar project Triangulation | Na | Yes | Rules and procedures on who qualifies, - internal manual | One shot, Case study | one time | Semi structured interviews, desk study | Qualitative and Quantitative; descriptive statistics
| 1.C. Who (stakeholders of the Neighbourhood Committee) was engaged in the identification process of the selection? | D | Comparison with evaluation of similar project | Na | Na | Terms of reference of the stakeholders (neighbourhood committee) | Case study, focus group | one time | desk study | Qualitative descriptive statistics
2. Was the program effective in distributing benefits to eligible beneficiaries? |  | N
| 2.A. What is progress over time of the proportion of applicants that received benefits? | D | Number of applications and number of benefits awarded/rejected | Na | Yes (0) | Data base contains the people that applied and registered as well as the ones that received benefits | Longitudinal | Non-Random sample | Secondary data analysis | Quantitative, descriptive statistics
| 2.B. Have errors in distribution occurred? (in other words: were eligible applicants excluded and some beneficiaries wrongly included?) | D | Threshold criterion (or error : wrong inclusion or exclusion) | Na | Na | Sample of appraisal documents (detective work), semi-structured interview | Causal tracing strategies | Random sample | Semi structured interviews, secondary data analysis | Quantitative and Qualitative, descriptive statistics
| 2.C Have the eligibility guidelines allowed the selection of the right people? (in other words: were the guidelines appropriate?) | N | Errors (inclusion/exclusion) | O% | Na | Project team of selected urban areas, members of neighbourhood committee | Focus groups, causal tracing strategies | Non-random sample | Semi structured interviews | Qualitative
3. Did the program meet the objective of training sufficient officials per each urban area? (to assure efficient distribution of the stipends) |  | N
| 3.A What was the drop-out rate of trained officials in the program? | D | drop-out rate of the officials that have been receiving training | None set, implicate standard is that is should be low | yes | Employee list | One shot | Census | Secondary data analysis | Coding Quantitative Data (code O= left program and code 1= still in the program) | The records in the database contain information of the officials that were fired or that resigned.
| 3.B What percentage of the officials involved into program finished the training per each urban area? | D | Amount of participants in the training versus targeted number of officials in the program | None set, implicit standard is that is should be low | Na | Subscription documents for the training, participant list | One shot | Census | Secondary data analysis | Coding Quantitative Data (code O= left training and code 1= finished training) | The records in the database contain information of the training participation of all officials.
4. To what extent did the program influence the economic activities of the eligible group? |  | C/E
| 4. A What was the effect of benefits distribution on unemployment rate among the eligible group? | C/E | Unemployment rate (in areas with and without intervention) | Yes / assumption to decrease the rate | yes | Database of the regional authorities | Interrupted Time series with comparison group | Census | Secondary data analysis, Expert judgment | Quantitative, descriptive, interpretation of association | Need to validate the information in the records.
| 4. B What was the effect of benefits distribution on involvement of beneficiaries in the black market? | C/E | Change in % on black market | Na | yes | Interviews | Before and after design without comparison group | Random sample | Notes of interviews, Expert judgment | Qualitative
| 4. C What was the effect of benefits distribution on the number of (registered) self-employed within the eligible group? | C/E | Number of registered entrepreneurs | Na | yes | Database of the regional authorities | Interrupted Time series | Census | Secondary data analysis, Expert judgment | Quantitative, descriptive, interpretation of association (correlation) | Need to validate the information in the records.
5. What was the effect of the benefit distribution scheme in terms of population growth? |  | C/E
| 5.A Did the programme cause a disproportionate change in the birth rate in the selected areas in comparison to other areas where there was no program? | D | birth rate | na | yes | Database of the regional authorities | Quasi -experimental, before and after | Census | Secondary data analysis, Expert judgment | Descriptive statistics, interpretation of association (correlation) | Need to validate the information in the records.
| 5.B Has there been an increase in the number of applications coming from immigrants to the urban areas? | D | immigration rate, number of applications | na | yes | Database of the regional authorities | Quasi-experimental, before and after | Census | Secondary data analysis, Expert judgment | Descriptive statistics, interpretation of association (correlation) | Need to validate the information in the records.
BONUS. How did the living conditions of the eligible group change because of this program? |  | C/E
| 6a. How did the household/consumer basket change for the eligible group by the end of the program? | D | Composition of the household basket (other-more products than before, or not) | Na | yes | Surveys filled out by respondents | Before and after design with comparison group | Random sample | Survey | Qualitative and quantitative data analysis
| 6b. Are the beneficiaries happier? | D | Amount of suicides Mental health indicator Amount of smiles Amount of parties | Na | yes | Statistics on suicides from regional authorities and interviews and observations with cameras | Before and after design without comparison group | Random sample for structured interviews | Secondary data analysis, Expert judgment (psychologist) | Qualitative and quantitative data analysis | Need to validate the information in the records.
Note on A1: Jan Černík:

## List2
SUB questions: | 1.B. What were the criteria for selection ? | 2.B. Have errors in distribution occurred? (in other words: were eligible applicants excluded and some beneficiaries wrongly included?) | 4. A What was the effect of benefits distribution on unemployment rate among the eligible group?
Measure or indicators: | Comparison with evaluation of similar project Triangulation | Threshold criterion (or error : wrong inclusion or exclusion) | Unemployment rate (in areas with and without intervention)
Data Sources: | Rules and procedures on who qualifies, - internal manual | Sample of appraisal documents (detective work), semi-structured interview | Database of the regional authorities
Design: | One shot, Case study | Causal tracing strategies | Interrupted Time series with comparison group
Sample: | one time | Random sample | Census
Data collection Instrument: | Semi structured interviews, desk study | Semi structured interviews, secondary data analysis | Secondary data analysis, Expert judgment
Data Analysis: | Qualitative and Quantitative; descriptive statistics | Quantitative and Qualitative, descriptive statistics | Quantitative, descriptive, interpretation of association